## Slide 1: Promoting transparency and financial sustainability of regional policies, state-owned enterprises and local authorities in Moldova
Peter Golias, INEKO Director
October 19th, 2017, Chisinau, Moldova
Project kick-off seminar

## Slide 2: About project
Duration: September 2017 – March 2019
Implemented by: INEKO in partnership with IDIS "Viitorul"
Funded by: The Official Development Assistance of the Slovak Republic (SlovakAid)
Follow-up on the project „Transparent, Financially Healthy and Competitive Self-governments in Moldova“ running since October 2015

## Slide 3: Project goals
Goal: To improve the transparency and financial stability of local governments and state-owned enterprises by transferring know-how from projects implemented in Slovakia
Objectives:
  Regular expert evaluation of regional policies
  Evaluating transparency and financial health of 50 biggest state-owned enterprises
  Updating financial data and transparency rating of local governments on existing web portals http://localbudgets.viitorul.org/ and http://localtransparency.viitorul.org/

## Slide 4: Timeline 1/4
Regular expert evaluation of regional policies
  November 2017: Methodology
  December 2018: Case studies from Slovakia
  Continuous: Monitoring and evaluating regional policies with outputs published in January 2018, April 2018, July 2018, October 2018, and February 2019

## Slide 5: Timeline 2/4
Evaluating transparency of 50 biggest state-owned enterprises
  November 2017: Methodology
  April 2018: Case studies from Slovakia
  May – October 2018: Data collection and processing
  November 2018 – February 2019: Creating a new web portal
  February 2019: Final conference in Chisinau, publishing results

## Slide 6: Timeline 3/4
Evaluating financial health of 50 biggest state-owned enterprises
  November 2017: Methodology
  January 2018: Case studies from Slovakia
  November 2017 – March 2018: Data collection and processing
  April 2018 – June 2018: Creating a new web portal
  June 2018: Seminar in Chisinau, publishing results

## Slide 7: Timeline 4/4
Updating financial data and transparency rating of local governments
  March – June 2018: Data collection
  July 2018 – September 2018: Updating web portals
  September – October 2018: Writing and publishing analysis of at least 20 pages on y/y changes
  October 2018: Seminar in Chisinau

## Slide 8: Key milestones
  Publishing results of evaluating regional poicies:
    January 2018, April 2018, July 2018, October 2018, February 2019
  Launching portal on financial health of 50 biggest state-owned enterprises:
    June 2018: Seminar in Chisinau
  Publishing updated portals and analysis on financial data and transparency rating of local governments
    October 2018: Seminar in Chisinau
  Launching portal on transparency of 50 biggest state-owned enterprises:
    February 2019: Final conference in Chisinau

## Slide 9: Evaluation of regional policies
Regional measures proposed or implemented by local authorities
Altogether, at least 30 regulations will be evaluated by at least 15 Experts over October 2017 – February 2019
The evaluations will be made on quarterly basis with results to be published for 5 quarters in: January 2018, April 2018, July 2018, October 2018, and February 2019

## Slide 10: Activities 1/4
IDIS: Research on competencies of local governments and mapping the areas of regulations suitable for regular expert assessments in Moldova
    Output: Writing summary of at least 5 pages
    Deadline: November 15th 2017
INEKO: Research on the best and the worst examples of regional measures evaluated in Slovakia
    Output: Writing summary of at least 10 pages
    Deadline: December 31st 2017
INEKO + IDIS: Developing methodology for regular expert assessment of regional socio-economic measures in Moldova
    Output: Methodology document of at least 5 pages
    Deadline: November 15th 2017

## Slide 11: Activities 2/4
IDIS: Creating the project webpage on http://viitorul.org/
    Deadline: January 2018
IDIS: Creating the team of Experts for regular evaluation of measures
    Output: List of at least 15 experts independent from local and central government – local activists, NGO experts, economic analysts, people from academy, sociologists, political scientists, etc.
    Deadline: November 15th 2017
IDIS + Experts: Continuous monitoring of regional measures proposed or implemented by local authorities

## Slide 12: Activities 3/4
IDIS: Selecting key measures to be evaluated every quarter and writing short characteristics of them
    Output: List of at least 30 measures and their characteristics during 5 quarters: Q4 2017 – Q4 2018
    Deadline: January 2018, April 2018, July 2018, October 2018, and February 2019
IDIS + Experts: Regular (quarterly) submitting of questionnaire with selected measures and their characteristics for evaluation to the panel of independent experts; evaluation
    Deadline: January 2018, April 2018, July 2018, October 2018, and February 2019

## Slide 13: Activities 4/4
IDIS: Collecting and processing results of evaluation, calculating ratings
    Deadline: January 2018, April 2018, July 2018, October 2018, and February 2019
IDIS: Publishing results via press-report and the project web page
    Deadline: January 2018, April 2018, July 2018, October 2018, and February 2019

## Slide 14: Methodology
Quality of the Measure [-3; +3]
Importance of the Measure for the Society and Economy (%)
Experts’ Comments on Evaluated Measures
Rating of the Measure [-300; +300]
  The average quality grade of the measure is multiplied by a coefficient expressing the average value of the measure’s importance

## Slide 15: Best practices
Examples of top measures from Slovakia:
  Electronic auctions
  Publishing subsidies/contracts on internet (searchable)
  Creating and publishing rules for giving subsidies, social flats or any handling with public assets
  Open/Internet communication with citizens
  Introducing and enforcing separated waste
  Integration of Roma minority or poor people
  Providing free internet access in public spaces
  Participative budgeting, launching business incubators
  Long-term investment plans, etc.

## Slide 16: Worst practices
Examples of the worst measures from Slovakia:
  Non-transparent public procurement, privatization
  Non-transparent provision of subsidies, public flats, rewards, etc.
  Abusing public media for political campaigns
  Important decisions (e.g. construction in the city center) without sufficient public dialogue
  Clientelism – preferential treatment of preferred suppliers
  Limitations to freedom on information
  Forced movement of problematic citizens (debtors) outside the municipality

## Slide 17: Time for discussion